## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | I. RDMP RU V BALIKPAPAN | 714.3 days | November 1, 2017 8:00 AM | July 28, 2020 10:24 AM |  | 1
2 | Yes | Auto Scheduled | Flare Stack BPP-II, Acid, RDMP | 672.3 days | November 1, 2017 8:00 AM | May 29, 2020 10:24 AM |  | 2
3 | Yes | Auto Scheduled | Penyusunan TOR | 22 days | November 1, 2017 8:00 AM | November 30, 2017 5:00 PM |  | 3
4 | Yes | Auto Scheduled | TOR selesai | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 3 | 3
5 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 4, 2017 8:00 AM | December 4, 2017 5:00 PM | 4 | 3
6 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 5, 2017 8:00 AM | January 2, 2018 5:00 PM | 5 | 3
7 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 3, 2018 8:00 AM | January 3, 2018 5:00 PM | 6 | 3
8 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 7 | 3
9 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 7, 2018 8:00 AM | May 3, 2018 5:00 PM | 8FS+2d | 3
10 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 3, 2018 8:00 AM | May 3, 2018 5:00 PM | 9FF | 3
11 | Yes | Auto Scheduled | EPC Work | 25.3 mons | May 17, 2018 8:00 AM | May 29, 2020 10:24 AM | 10FS+9d | 3
12 | Yes | Auto Scheduled | Demolish Acid Flare | 0 days | July 1, 2020 10:24 AM | July 1, 2020 10:24 AM |  | 2
13 | Yes | Manually Scheduled | Demolish Acid Flare | 0 days | July 1, 2020 10:24 AM | July 1, 2020 10:24 AM | 11FS+23d,26FS+23d,32FS+23d,62FS+23d | 3
14 | Yes | Auto Scheduled | Demolish BPP-II Flare | 0 days | July 28, 2020 10:24 AM | July 28, 2020 10:24 AM |  | 2
15 | Yes | Manually Scheduled | Demolish BPP-II Flare | 0 days | July 28, 2020 10:24 AM | July 28, 2020 10:24 AM | 13FS+19d | 3
16 | [7 empty] | 3
17 | Yes | Auto Scheduled | Site Development 2 | 390.1 days | November 1, 2017 8:00 AM | May 1, 2019 8:48 AM |  | 2
18 | Yes | Auto Scheduled | Penyusunan TOR | 22 days | November 1, 2017 8:00 AM | November 30, 2017 5:00 PM |  | 3
19 | Yes | Auto Scheduled | TOR selesai | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 18 | 3
20 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 4, 2017 8:00 AM | December 4, 2017 5:00 PM | 19 | 3
21 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 5, 2017 8:00 AM | January 2, 2018 5:00 PM | 20 | 3
22 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 3, 2018 8:00 AM | January 3, 2018 5:00 PM | 21 | 3
23 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 22 | 3
24 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 7, 2018 8:00 AM | May 3, 2018 5:00 PM | 23FS+2d | 3
25 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 3, 2018 8:00 AM | May 3, 2018 5:00 PM | 24FF | 3
26 | Yes | Auto Scheduled | EPC Work | 12.1 mons | May 10, 2018 8:00 AM | May 1, 2019 8:48 AM | 25FS+4d | 3
27 | [7 empty] | 3
28 | Yes | Auto Scheduled | Temporary Dock/ Jetty | 325.1 days | November 1, 2017 8:00 AM | January 30, 2019 8:48 AM |  | 2
29 | Yes | Auto Scheduled | Dokumen final ITB menunggu hasil Traffic & Logistic Study | 45 days | November 1, 2017 8:00 AM | January 2, 2018 5:00 PM |  | 3
30 | Yes | Auto Scheduled | Bidding EPC | 2 mons | January 3, 2018 8:00 AM | March 1, 2018 5:00 PM | 29 | 3
31 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | March 2, 2018 8:00 AM | March 2, 2018 5:00 PM | 30 | 3
32 | Yes | Auto Scheduled | EPC Work | 11.1 mons | March 9, 2018 8:00 AM | January 30, 2019 8:48 AM | 31FS+4d | 3
33 | [7 empty] | 3
34 | Yes | Auto Scheduled | Laboratorium | 295.9 days | November 1, 2017 8:00 AM | December 19, 2018 4:12 PM |  | 2
35 | Yes | Auto Scheduled | Design Struktur oleh LAPI | 52.5 days | November 1, 2017 8:00 AM | January 12, 2018 12:00 PM |  | 3
36 | Yes | Auto Scheduled | Contract Addendum Konsultan | 20 days | November 1, 2017 8:00 AM | November 28, 2017 5:00 PM |  | 4
37 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2.5 mons | November 1, 2017 8:00 AM | January 12, 2018 12:00 PM |  | 4
38 | Yes | Auto Scheduled | Design Interior oleh MSS | 63 days | November 1, 2017 8:00 AM | January 26, 2018 5:00 PM |  | 3
39 | Yes | Auto Scheduled | Contract Addendum Konsultan | 20 days | November 1, 2017 8:00 AM | November 28, 2017 5:00 PM |  | 4
40 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 3 mons | November 1, 2017 8:00 AM | January 26, 2018 5:00 PM | 37FF+10d | 4
41 | Yes | Auto Scheduled | Bidding EPC | 2 mons | January 29, 2018 8:00 AM | March 27, 2018 5:00 PM | 40,37 | 3
42 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | March 27, 2018 8:00 AM | March 27, 2018 5:00 PM | 41FF | 3
43 | Yes | Auto Scheduled | EPC Work | 8.9 mons | April 3, 2018 8:00 AM | December 19, 2018 4:12 PM | 42FS+4d | 3
44 | [7 empty] | 3
45 | Yes | Auto Scheduled | Workshop dan Warehouse | 379.9 days | November 1, 2017 8:00 AM | April 16, 2019 4:12 PM |  | 2
46 | Yes | Auto Scheduled | Contract Addendum Konsultan | 24 days | November 1, 2017 8:00 AM | December 4, 2017 5:00 PM |  | 3
47 | Yes | Auto Scheduled | Site Visit | 3 days | November 21, 2017 8:00 AM | November 23, 2017 5:00 PM |  | 3
48 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 3 mons | November 1, 2017 8:00 AM | January 26, 2018 5:00 PM | 46SS | 3
49 | Yes | Auto Scheduled | Bidding EPC | 2 mons | January 29, 2018 8:00 AM | March 27, 2018 5:00 PM | 48 | 3
50 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | March 27, 2018 8:00 AM | March 27, 2018 5:00 PM | 49FF | 3
51 | Yes | Auto Scheduled | EPC Work | 12.9 mons | April 3, 2018 8:00 AM | April 16, 2019 4:12 PM | 50FS+4d | 3
52 | [7 empty] | 3
53 | Yes | Auto Scheduled | Reroute Jl. Yos Sudarso | 402.8 days | November 1, 2017 8:00 AM | May 17, 2019 3:24 PM |  | 2
54 | Yes | Auto Scheduled | Penyusunan TOR | 22 days | November 1, 2017 8:00 AM | November 30, 2017 5:00 PM |  | 3
55 | Yes | Auto Scheduled | TOR selesai | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 54 | 3
56 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 4, 2017 8:00 AM | December 4, 2017 5:00 PM | 55 | 3
57 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 5, 2017 8:00 AM | January 2, 2018 5:00 PM | 56 | 3
58 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 3, 2018 8:00 AM | January 3, 2018 5:00 PM | 57 | 3
59 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 58 | 3
60 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 5, 2018 8:00 AM | May 1, 2018 5:00 PM | 59 | 3
61 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 60FF | 3
62 | Yes | Auto Scheduled | EPC Work | 12.8 mons | May 8, 2018 8:00 AM | May 17, 2019 3:24 PM | 61FS+4d | 3
63 | [7 empty] | 3
64 | Yes | Auto Scheduled | RDMP Office | 379.8 days | November 14, 2017 8:00 AM | April 29, 2019 3:24 PM |  | 2
65 | Yes | Auto Scheduled | TOR selesai | 1 day | November 14, 2017 8:00 AM | November 14, 2017 5:00 PM |  | 3
66 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | November 15, 2017 8:00 AM | November 15, 2017 5:00 PM | 65 | 3
67 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | November 16, 2017 8:00 AM | December 14, 2017 5:00 PM | 66 | 3
68 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | December 15, 2017 8:00 AM | December 15, 2017 5:00 PM | 67 | 3
69 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | December 18, 2017 8:00 AM | February 13, 2018 5:00 PM | 68 | 3
70 | Yes | Auto Scheduled | Bidding EPC | 2 mons | February 14, 2018 8:00 AM | April 12, 2018 5:00 PM | 69 | 3
71 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | April 12, 2018 8:00 AM | April 12, 2018 5:00 PM | 70FF | 3
72 | Yes | Auto Scheduled | EPC Work | 12.8 mons | April 18, 2018 8:00 AM | April 29, 2019 3:24 PM | 71FS+3d | 3
73 | [7 empty] | 3
74 | Yes | Auto Scheduled | HSSE Office | 364.1 days | November 14, 2017 8:00 AM | April 8, 2019 8:48 AM |  | 2
75 | Yes | Auto Scheduled | TOR selesai | 1 day | November 14, 2017 8:00 AM | November 14, 2017 5:00 PM |  | 3
76 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | November 15, 2017 8:00 AM | November 15, 2017 5:00 PM | 75 | 3
77 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | November 16, 2017 8:00 AM | December 14, 2017 5:00 PM | 76 | 3
78 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | December 15, 2017 8:00 AM | December 15, 2017 5:00 PM | 77 | 3
79 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | December 18, 2017 8:00 AM | February 13, 2018 5:00 PM | 78 | 3
80 | Yes | Auto Scheduled | Bidding EPC | 2 mons | February 14, 2018 8:00 AM | April 12, 2018 5:00 PM | 79 | 3
81 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | April 12, 2018 8:00 AM | April 12, 2018 5:00 PM | 80FF | 3
82 | Yes | Auto Scheduled | EPC Work | 12.1 mons | April 17, 2018 8:00 AM | April 8, 2019 8:48 AM | 81FS+2d | 3
83 | [7 empty] | 3
84 | Yes | Auto Scheduled | Apartment Tahap-2 | 473.2 days | November 1, 2017 8:00 AM | August 26, 2019 9:36 AM |  | 2
85 | Yes | Auto Scheduled | Draft SOW selesai | 14 days | November 1, 2017 8:00 AM | November 20, 2017 5:00 PM |  | 3
86 | Yes | Auto Scheduled | Workshop dan Finalisasi SOW | 1 day | November 21, 2017 8:00 AM | November 21, 2017 5:00 PM | 85 | 3
87 | Yes | Auto Scheduled | TOR selesai | 1 day | November 22, 2017 8:00 AM | November 22, 2017 5:00 PM | 86 | 3
88 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 4 days | November 23, 2017 8:00 AM | November 28, 2017 5:00 PM | 87 | 3
89 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | November 29, 2017 8:00 AM | December 27, 2017 5:00 PM | 88 | 3
90 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | December 28, 2017 8:00 AM | December 28, 2017 5:00 PM | 89 | 3
91 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | December 29, 2017 8:00 AM | February 26, 2018 5:00 PM | 90 | 3
92 | Yes | Auto Scheduled | Bidding EPC | 2 mons | February 27, 2018 8:00 AM | April 25, 2018 5:00 PM | 91 | 3
93 | Yes | Auto Scheduled | Contract Award EPC & KOM | 2 days | April 26, 2018 8:00 AM | April 27, 2018 5:00 PM | 92 | 3
94 | Yes | Auto Scheduled | EPC Work | 16.2 mons | May 7, 2018 8:00 AM | August 26, 2019 9:36 AM | 93FS+5d | 3
95 | [7 empty] | 3
96 | Yes | Auto Scheduled | Sulfur Jetty | 327.2 days | November 1, 2017 8:00 AM | February 1, 2019 9:36 AM |  | 2
97 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
98 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 97 | 3
99 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 98 | 3
100 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 99 | 3
101 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 100 | 3
102 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 101FS+1d | 3
103 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 6, 2018 8:00 AM | May 2, 2018 5:00 PM | 102FS+1d | 3
104 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 2, 2018 8:00 AM | May 2, 2018 5:00 PM | 103FF | 3
105 | Yes | Auto Scheduled | EPC Work | 9.2 mons | May 8, 2018 8:00 AM | February 1, 2019 9:36 AM | 104FS+3d | 3
106 | [7 empty] | 3
107 | Yes | Auto Scheduled | Revitalisasi Jetty | 327.2 days | November 1, 2017 8:00 AM | February 1, 2019 9:36 AM |  | 2
108 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
109 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 108 | 3
110 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 109 | 3
111 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 110 | 3
112 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 111 | 3
113 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 112FS+1d | 3
114 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 6, 2018 8:00 AM | May 2, 2018 5:00 PM | 113FS+1d | 3
115 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 2, 2018 8:00 AM | May 2, 2018 5:00 PM | 114FF | 3
116 | Yes | Auto Scheduled | EPC Work | 9.2 mons | May 8, 2018 8:00 AM | February 1, 2019 9:36 AM | 115FS+3d | 3
117 | [7 empty] | 3
118 | Yes | Auto Scheduled | Renovasi Kantor UP | 227.6 days | November 14, 2017 8:00 AM | September 27, 2018 1:48 PM |  | 2
119 | Yes | Auto Scheduled | TOR selesai | 1 day | November 14, 2017 8:00 AM | November 14, 2017 5:00 PM |  | 3
120 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | November 15, 2017 8:00 AM | November 15, 2017 5:00 PM | 119 | 3
121 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | November 16, 2017 8:00 AM | December 14, 2017 5:00 PM | 120 | 3
122 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | December 15, 2017 8:00 AM | December 15, 2017 5:00 PM | 121 | 3
123 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | December 18, 2017 8:00 AM | February 13, 2018 5:00 PM | 122 | 3
124 | Yes | Auto Scheduled | Bidding EPC | 2 mons | February 14, 2018 8:00 AM | April 12, 2018 5:00 PM | 123 | 3
125 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | April 12, 2018 8:00 AM | April 12, 2018 5:00 PM | 124FF | 3
126 | Yes | Auto Scheduled | EPC Work | 5.6 mons | April 17, 2018 8:00 AM | September 27, 2018 1:48 PM | 125FS+2d | 3
127 | [7 empty] | 3
128 | Yes | Auto Scheduled | Pemompaan ke Tanjung Batu | 402.8 days | November 1, 2017 8:00 AM | May 17, 2019 3:24 PM |  | 2
129 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
130 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 129 | 3
131 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 130 | 3
132 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 131 | 3
133 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 132 | 3
134 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 133FS+1d | 3
135 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 5, 2018 8:00 AM | May 1, 2018 5:00 PM | 134 | 3
136 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 135FF | 3
137 | Yes | Auto Scheduled | EPC Work | 12.8 mons | May 8, 2018 8:00 AM | May 17, 2019 3:24 PM | 136FS+4d | 3
138 | [7 empty] | 3
139 | Yes | Auto Scheduled | Bendali Apartemen | 282.1 days | November 1, 2017 8:00 AM | November 30, 2018 8:48 AM |  | 2
140 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
141 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 140 | 3
142 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 141 | 3
143 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 142 | 3
144 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 143 | 3
145 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 144FS+1d | 3
146 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 5, 2018 8:00 AM | May 1, 2018 5:00 PM | 145 | 3
147 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 146FF | 3
148 | Yes | Auto Scheduled | EPC Work | 7.1 mons | May 7, 2018 8:00 AM | November 30, 2018 8:48 AM | 147FS+3d | 3
149 | [7 empty] | 3
150 | Yes | Auto Scheduled | Pengendalian Banjir | 282.1 days | November 1, 2017 8:00 AM | November 30, 2018 8:48 AM |  | 2
151 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
152 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 151 | 3
153 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 152 | 3
154 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 153 | 3
155 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 154 | 3
156 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 155FS+1d | 3
157 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 5, 2018 8:00 AM | May 1, 2018 5:00 PM | 156 | 3
158 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 157FF | 3
159 | Yes | Auto Scheduled | EPC Work | 7.1 mons | May 7, 2018 8:00 AM | November 30, 2018 8:48 AM | 158FS+3d | 3
160 | [7 empty] | 3
161 | Yes | Auto Scheduled | Unforeseen Material | 282.1 days | November 1, 2017 8:00 AM | November 30, 2018 8:48 AM |  | 2
162 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
163 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 162 | 3
164 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 163 | 3
165 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 164 | 3
166 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 165 | 3
167 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 166FS+1d | 3
168 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 5, 2018 8:00 AM | May 1, 2018 5:00 PM | 167 | 3
169 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 168FF | 3
170 | Yes | Auto Scheduled | EPC Work | 7.1 mons | May 7, 2018 8:00 AM | November 30, 2018 8:48 AM | 169FS+3d | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | ABS | A | Work |  |  |  |  | 100% | $0.00/h | 0
2 | SLP | S | Work |  |  |  |  | 100% | $0.00/h | 0
3 | DW | D | Work |  |  |  |  | 100% | $0.00/h | 0
4 | TM | T | Work |  |  |  |  | 100% | $0.00/h | 0
5 | BF | B | Work |  |  |  |  | 100% | $0.00/h | 0
6 | TSI | T | Work |  |  |  |  | 100% | $0.00/h | 0
7 | WS | W | Work |  |  |  |  | 100% | $0.00/h | 0
8 | MA | M | Work |  |  |  |  | 100% | $0.00/h | 0
9 | AF | A | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Laboratorium | ABS | 0 | 2,367.2h | 100%
Workshop dan Warehouse | BF | 0 | 3,039.2h | 100%
Reroute Jl. Yos Sudarso | ABS | 0 | 3,222.4h | 100%
RDMP Office | ABS | 0 | 3,038.4h | 100%
HSSE Office | TM | 0 | 2,912.8h | 100%
Apartment Tahap-2 | DW | 0 | 3,785.6h | 100%
Apartment Tahap-2 | AF | 0 | 3,785.6h | 100%
Sulfur Jetty | WS | 0 | 2,617.6h | 100%
Revitalisasi Jetty | WS | 0 | 2,617.6h | 100%
Pengendalian Banjir | ABS | 0 | 2,256.8h | 100%
Unforeseen Material | ABS | 0 | 2,256.8h | 100%

## Holidays
Holidays
January 1,2017
January 3,2017
March 30,2017
April 2,2017
May 1,2017
May 10,2017
May 21,2017
May 31,2017
August 15,2017
October 3,2017
October 31,2017
November 1,2017
November 21,2017
December 25,2017
December 26,2017