## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | I. RDMP RU V BALIKPAPAN | 714.3 days | November 1, 2017 8:00 AM | July 28, 2020 10:24 AM |  | 1
2 | Yes | Auto Scheduled | Flare Stack BPP-II, Acid, RDMP | 672.3 days | November 1, 2017 8:00 AM | May 29, 2020 10:24 AM |  | 2
3 | Yes | Auto Scheduled | Penyusunan TOR | 22 days | November 1, 2017 8:00 AM | November 30, 2017 5:00 PM |  | 3
4 | Yes | Auto Scheduled | TOR selesai | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 3 | 3
5 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 4, 2017 8:00 AM | December 4, 2017 5:00 PM | 4 | 3
6 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 5, 2017 8:00 AM | January 2, 2018 5:00 PM | 5 | 3
7 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 3, 2018 8:00 AM | January 3, 2018 5:00 PM | 6 | 3
8 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 7 | 3
9 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 7, 2018 8:00 AM | May 3, 2018 5:00 PM | 8FS+2d | 3
10 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 3, 2018 8:00 AM | May 3, 2018 5:00 PM | 9FF | 3
11 | Yes | Auto Scheduled | EPC Work | 25.3 mons | May 17, 2018 8:00 AM | May 29, 2020 10:24 AM | 10FS+9d | 3
12 | Yes | Auto Scheduled | Demolish Acid Flare | 0 days | July 1, 2020 10:24 AM | July 1, 2020 10:24 AM |  | 2
13 | Yes | Manually Scheduled | Demolish Acid Flare | 0 days | July 1, 2020 10:24 AM | July 1, 2020 10:24 AM | 11FS+23d,26FS+23d,32FS+23d,62FS+23d | 3
14 | Yes | Auto Scheduled | Demolish BPP-II Flare | 0 days | July 28, 2020 10:24 AM | July 28, 2020 10:24 AM |  | 2
15 | Yes | Manually Scheduled | Demolish BPP-II Flare | 0 days | July 28, 2020 10:24 AM | July 28, 2020 10:24 AM | 13FS+19d | 3
16 | [7 empty] | 3
17 | Yes | Auto Scheduled | Site Development 2 | 390.1 days | November 1, 2017 8:00 AM | May 1, 2019 8:48 AM |  | 2
18 | Yes | Auto Scheduled | Penyusunan TOR | 22 days | November 1, 2017 8:00 AM | November 30, 2017 5:00 PM |  | 3
19 | Yes | Auto Scheduled | TOR selesai | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 18 | 3
20 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 4, 2017 8:00 AM | December 4, 2017 5:00 PM | 19 | 3
21 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 5, 2017 8:00 AM | January 2, 2018 5:00 PM | 20 | 3
22 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 3, 2018 8:00 AM | January 3, 2018 5:00 PM | 21 | 3
23 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 22 | 3
24 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 7, 2018 8:00 AM | May 3, 2018 5:00 PM | 23FS+2d | 3
25 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 3, 2018 8:00 AM | May 3, 2018 5:00 PM | 24FF | 3
26 | Yes | Auto Scheduled | EPC Work | 12.1 mons | May 10, 2018 8:00 AM | May 1, 2019 8:48 AM | 25FS+4d | 3
27 | [7 empty] | 3
28 | Yes | Auto Scheduled | Temporary Dock/ Jetty | 325.1 days | November 1, 2017 8:00 AM | January 30, 2019 8:48 AM |  | 2
29 | Yes | Auto Scheduled | Dokumen final ITB menunggu hasil Traffic & Logistic Study | 45 days | November 1, 2017 8:00 AM | January 2, 2018 5:00 PM |  | 3
30 | Yes | Auto Scheduled | Bidding EPC | 2 mons | January 3, 2018 8:00 AM | March 1, 2018 5:00 PM | 29 | 3
31 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | March 2, 2018 8:00 AM | March 2, 2018 5:00 PM | 30 | 3
32 | Yes | Auto Scheduled | EPC Work | 11.1 mons | March 9, 2018 8:00 AM | January 30, 2019 8:48 AM | 31FS+4d | 3
33 | [7 empty] | 3
34 | Yes | Auto Scheduled | Laboratorium | 295.9 days | November 1, 2017 8:00 AM | December 19, 2018 4:12 PM |  | 2
35 | Yes | Auto Scheduled | Design Struktur oleh LAPI | 52.5 days | November 1, 2017 8:00 AM | January 12, 2018 12:00 PM |  | 3
36 | Yes | Auto Scheduled | Contract Addendum Konsultan | 20 days | November 1, 2017 8:00 AM | November 28, 2017 5:00 PM |  | 4
37 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2.5 mons | November 1, 2017 8:00 AM | January 12, 2018 12:00 PM |  | 4
38 | Yes | Auto Scheduled | Design Interior oleh MSS | 63 days | November 1, 2017 8:00 AM | January 26, 2018 5:00 PM |  | 3
39 | Yes | Auto Scheduled | Contract Addendum Konsultan | 20 days | November 1, 2017 8:00 AM | November 28, 2017 5:00 PM |  | 4
40 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 3 mons | November 1, 2017 8:00 AM | January 26, 2018 5:00 PM | 37FF+10d | 4
41 | Yes | Auto Scheduled | Bidding EPC | 2 mons | January 29, 2018 8:00 AM | March 27, 2018 5:00 PM | 40,37 | 3
42 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | March 27, 2018 8:00 AM | March 27, 2018 5:00 PM | 41FF | 3
43 | Yes | Auto Scheduled | EPC Work | 8.9 mons | April 3, 2018 8:00 AM | December 19, 2018 4:12 PM | 42FS+4d | 3
44 | [7 empty] | 3
45 | Yes | Auto Scheduled | Workshop dan Warehouse | 379.9 days | November 1, 2017 8:00 AM | April 16, 2019 4:12 PM |  | 2
46 | Yes | Auto Scheduled | Contract Addendum Konsultan | 24 days | November 1, 2017 8:00 AM | December 4, 2017 5:00 PM |  | 3
47 | Yes | Auto Scheduled | Site Visit | 3 days | November 21, 2017 8:00 AM | November 23, 2017 5:00 PM |  | 3
48 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 3 mons | November 1, 2017 8:00 AM | January 26, 2018 5:00 PM | 46SS | 3
49 | Yes | Auto Scheduled | Bidding EPC | 2 mons | January 29, 2018 8:00 AM | March 27, 2018 5:00 PM | 48 | 3
50 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | March 27, 2018 8:00 AM | March 27, 2018 5:00 PM | 49FF | 3
51 | Yes | Auto Scheduled | EPC Work | 12.9 mons | April 3, 2018 8:00 AM | April 16, 2019 4:12 PM | 50FS+4d | 3
52 | [7 empty] | 3
53 | Yes | Auto Scheduled | Reroute Jl. Yos Sudarso | 402.8 days | November 1, 2017 8:00 AM | May 17, 2019 3:24 PM |  | 2
54 | Yes | Auto Scheduled | Penyusunan TOR | 22 days | November 1, 2017 8:00 AM | November 30, 2017 5:00 PM |  | 3
55 | Yes | Auto Scheduled | TOR selesai | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 54 | 3
56 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 4, 2017 8:00 AM | December 4, 2017 5:00 PM | 55 | 3
57 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 5, 2017 8:00 AM | January 2, 2018 5:00 PM | 56 | 3
58 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 3, 2018 8:00 AM | January 3, 2018 5:00 PM | 57 | 3
59 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 58 | 3
60 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 5, 2018 8:00 AM | May 1, 2018 5:00 PM | 59 | 3
61 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 60FF | 3
62 | Yes | Auto Scheduled | EPC Work | 12.8 mons | May 8, 2018 8:00 AM | May 17, 2019 3:24 PM | 61FS+4d | 3
63 | [7 empty] | 3
64 | Yes | Auto Scheduled | RDMP Office | 379.8 days | November 14, 2017 8:00 AM | April 29, 2019 3:24 PM |  | 2
65 | Yes | Auto Scheduled | TOR selesai | 1 day | November 14, 2017 8:00 AM | November 14, 2017 5:00 PM |  | 3
66 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | November 15, 2017 8:00 AM | November 15, 2017 5:00 PM | 65 | 3
67 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | November 16, 2017 8:00 AM | December 14, 2017 5:00 PM | 66 | 3
68 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | December 15, 2017 8:00 AM | December 15, 2017 5:00 PM | 67 | 3
69 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | December 18, 2017 8:00 AM | February 13, 2018 5:00 PM | 68 | 3
70 | Yes | Auto Scheduled | Bidding EPC | 2 mons | February 14, 2018 8:00 AM | April 12, 2018 5:00 PM | 69 | 3
71 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | April 12, 2018 8:00 AM | April 12, 2018 5:00 PM | 70FF | 3
72 | Yes | Auto Scheduled | EPC Work | 12.8 mons | April 18, 2018 8:00 AM | April 29, 2019 3:24 PM | 71FS+3d | 3
73 | [7 empty] | 3
74 | Yes | Auto Scheduled | HSSE Office | 364.1 days | November 14, 2017 8:00 AM | April 8, 2019 8:48 AM |  | 2
75 | Yes | Auto Scheduled | TOR selesai | 1 day | November 14, 2017 8:00 AM | November 14, 2017 5:00 PM |  | 3
76 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | November 15, 2017 8:00 AM | November 15, 2017 5:00 PM | 75 | 3
77 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | November 16, 2017 8:00 AM | December 14, 2017 5:00 PM | 76 | 3
78 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | December 15, 2017 8:00 AM | December 15, 2017 5:00 PM | 77 | 3
79 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | December 18, 2017 8:00 AM | February 13, 2018 5:00 PM | 78 | 3
80 | Yes | Auto Scheduled | Bidding EPC | 2 mons | February 14, 2018 8:00 AM | April 12, 2018 5:00 PM | 79 | 3
81 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | April 12, 2018 8:00 AM | April 12, 2018 5:00 PM | 80FF | 3
82 | Yes | Auto Scheduled | EPC Work | 12.1 mons | April 17, 2018 8:00 AM | April 8, 2019 8:48 AM | 81FS+2d | 3
83 | [7 empty] | 3
84 | Yes | Auto Scheduled | Apartment Tahap-2 | 473.2 days | November 1, 2017 8:00 AM | August 26, 2019 9:36 AM |  | 2
85 | Yes | Auto Scheduled | Draft SOW selesai | 14 days | November 1, 2017 8:00 AM | November 20, 2017 5:00 PM |  | 3
86 | Yes | Auto Scheduled | Workshop dan Finalisasi SOW | 1 day | November 21, 2017 8:00 AM | November 21, 2017 5:00 PM | 85 | 3
87 | Yes | Auto Scheduled | TOR selesai | 1 day | November 22, 2017 8:00 AM | November 22, 2017 5:00 PM | 86 | 3
88 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 4 days | November 23, 2017 8:00 AM | November 28, 2017 5:00 PM | 87 | 3
89 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | November 29, 2017 8:00 AM | December 27, 2017 5:00 PM | 88 | 3
90 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | December 28, 2017 8:00 AM | December 28, 2017 5:00 PM | 89 | 3
91 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | December 29, 2017 8:00 AM | February 26, 2018 5:00 PM | 90 | 3
92 | Yes | Auto Scheduled | Bidding EPC | 2 mons | February 27, 2018 8:00 AM | April 25, 2018 5:00 PM | 91 | 3
93 | Yes | Auto Scheduled | Contract Award EPC & KOM | 2 days | April 26, 2018 8:00 AM | April 27, 2018 5:00 PM | 92 | 3
94 | Yes | Auto Scheduled | EPC Work | 16.2 mons | May 7, 2018 8:00 AM | August 26, 2019 9:36 AM | 93FS+5d | 3
95 | [7 empty] | 3
96 | Yes | Auto Scheduled | Sulfur Jetty | 327.2 days | November 1, 2017 8:00 AM | February 1, 2019 9:36 AM |  | 2
97 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
98 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 97 | 3
99 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 98 | 3
100 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 99 | 3
101 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 100 | 3
102 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 101FS+1d | 3
103 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 6, 2018 8:00 AM | May 2, 2018 5:00 PM | 102FS+1d | 3
104 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 2, 2018 8:00 AM | May 2, 2018 5:00 PM | 103FF | 3
105 | Yes | Auto Scheduled | EPC Work | 9.2 mons | May 8, 2018 8:00 AM | February 1, 2019 9:36 AM | 104FS+3d | 3
106 | [7 empty] | 3
107 | Yes | Auto Scheduled | Revitalisasi Jetty | 327.2 days | November 1, 2017 8:00 AM | February 1, 2019 9:36 AM |  | 2
108 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
109 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 108 | 3
110 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 109 | 3
111 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 110 | 3
112 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 111 | 3
113 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 112FS+1d | 3
114 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 6, 2018 8:00 AM | May 2, 2018 5:00 PM | 113FS+1d | 3
115 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 2, 2018 8:00 AM | May 2, 2018 5:00 PM | 114FF | 3
116 | Yes | Auto Scheduled | EPC Work | 9.2 mons | May 8, 2018 8:00 AM | February 1, 2019 9:36 AM | 115FS+3d | 3
117 | [7 empty] | 3
118 | Yes | Auto Scheduled | Renovasi Kantor UP | 227.6 days | November 14, 2017 8:00 AM | September 27, 2018 1:48 PM |  | 2
119 | Yes | Auto Scheduled | TOR selesai | 1 day | November 14, 2017 8:00 AM | November 14, 2017 5:00 PM |  | 3
120 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | November 15, 2017 8:00 AM | November 15, 2017 5:00 PM | 119 | 3
121 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | November 16, 2017 8:00 AM | December 14, 2017 5:00 PM | 120 | 3
122 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | December 15, 2017 8:00 AM | December 15, 2017 5:00 PM | 121 | 3
123 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | December 18, 2017 8:00 AM | February 13, 2018 5:00 PM | 122 | 3
124 | Yes | Auto Scheduled | Bidding EPC | 2 mons | February 14, 2018 8:00 AM | April 12, 2018 5:00 PM | 123 | 3
125 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | April 12, 2018 8:00 AM | April 12, 2018 5:00 PM | 124FF | 3
126 | Yes | Auto Scheduled | EPC Work | 5.6 mons | April 17, 2018 8:00 AM | September 27, 2018 1:48 PM | 125FS+2d | 3
127 | [7 empty] | 3
128 | Yes | Auto Scheduled | Pemompaan ke Tanjung Batu | 402.8 days | November 1, 2017 8:00 AM | May 17, 2019 3:24 PM |  | 2
129 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
130 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 129 | 3
131 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 130 | 3
132 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 131 | 3
133 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 132 | 3
134 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 133FS+1d | 3
135 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 5, 2018 8:00 AM | May 1, 2018 5:00 PM | 134 | 3
136 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 135FF | 3
137 | Yes | Auto Scheduled | EPC Work | 12.8 mons | May 8, 2018 8:00 AM | May 17, 2019 3:24 PM | 136FS+4d | 3
138 | [7 empty] | 3
139 | Yes | Auto Scheduled | Bendali Apartemen | 282.1 days | November 1, 2017 8:00 AM | November 30, 2018 8:48 AM |  | 2
140 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
141 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 140 | 3
142 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 141 | 3
143 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 142 | 3
144 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 143 | 3
145 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 144FS+1d | 3
146 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 5, 2018 8:00 AM | May 1, 2018 5:00 PM | 145 | 3
147 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 146FF | 3
148 | Yes | Auto Scheduled | EPC Work | 7.1 mons | May 7, 2018 8:00 AM | November 30, 2018 8:48 AM | 147FS+3d | 3
149 | [7 empty] | 3
150 | Yes | Auto Scheduled | Pengendalian Banjir | 282.1 days | November 1, 2017 8:00 AM | November 30, 2018 8:48 AM |  | 2
151 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
152 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 151 | 3
153 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 152 | 3
154 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 153 | 3
155 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 154 | 3
156 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 155FS+1d | 3
157 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 5, 2018 8:00 AM | May 1, 2018 5:00 PM | 156 | 3
158 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 157FF | 3
159 | Yes | Auto Scheduled | EPC Work | 7.1 mons | May 7, 2018 8:00 AM | November 30, 2018 8:48 AM | 158FS+3d | 3
160 | [7 empty] | 3
161 | Yes | Auto Scheduled | Unforeseen Material | 282.1 days | November 1, 2017 8:00 AM | November 30, 2018 8:48 AM |  | 2
162 | Yes | Auto Scheduled | Penyusunan TOR | 21 days | November 1, 2017 8:00 AM | November 29, 2017 5:00 PM |  | 3
163 | Yes | Auto Scheduled | TOR selesai | 1 day | November 30, 2017 8:00 AM | November 30, 2017 5:00 PM | 162 | 3
164 | Yes | Auto Scheduled | TOR dikirim ke Procurement | 1 day | December 1, 2017 8:00 AM | December 1, 2017 5:00 PM | 163 | 3
165 | Yes | Auto Scheduled | Seleksi Konsultan | 1 mon | December 4, 2017 8:00 AM | January 1, 2018 5:00 PM | 164 | 3
166 | Yes | Auto Scheduled | Contract Award Konsultan & KOM | 1 day | January 2, 2018 8:00 AM | January 2, 2018 5:00 PM | 165 | 3
167 | Yes | Auto Scheduled | Design untuk SOW EPC & Paket Tender | 2 mons | January 4, 2018 8:00 AM | March 2, 2018 5:00 PM | 166FS+1d | 3
168 | Yes | Auto Scheduled | Bidding EPC | 2 mons | March 5, 2018 8:00 AM | May 1, 2018 5:00 PM | 167 | 3
169 | Yes | Auto Scheduled | Contract Award EPC & KOM | 1 day | May 1, 2018 8:00 AM | May 1, 2018 5:00 PM | 168FF | 3
170 | Yes | Auto Scheduled | EPC Work | 7.1 mons | May 7, 2018 8:00 AM | November 30, 2018 8:48 AM | 169FS+3d | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | ABS | A | Work |  |  |  |  | 100% | $0.00/h | 0
2 | SLP | S | Work |  |  |  |  | 100% | $0.00/h | 0
3 | DW | D | Work |  |  |  |  | 100% | $0.00/h | 0
4 | TM | T | Work |  |  |  |  | 100% | $0.00/h | 0
5 | BF | B | Work |  |  |  |  | 100% | $0.00/h | 0
6 | TSI | T | Work |  |  |  |  | 100% | $0.00/h | 0
7 | WS | W | Work |  |  |  |  | 100% | $0.00/h | 0
8 | MA | M | Work |  |  |  |  | 100% | $0.00/h | 0
9 | AF | A | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Laboratorium | ABS | 0 | 2,367.2h | 100%
Workshop dan Warehouse | BF | 0 | 3,039.2h | 100%
Reroute Jl. Yos Sudarso | ABS | 0 | 3,222.4h | 100%
RDMP Office | ABS | 0 | 3,038.4h | 100%
HSSE Office | TM | 0 | 2,912.8h | 100%
Apartment Tahap-2 | DW | 0 | 3,785.6h | 100%
Apartment Tahap-2 | AF | 0 | 3,785.6h | 100%
Sulfur Jetty | WS | 0 | 2,617.6h | 100%
Revitalisasi Jetty | WS | 0 | 2,617.6h | 100%
Pengendalian Banjir | ABS | 0 | 2,256.8h | 100%
Unforeseen Material | ABS | 0 | 2,256.8h | 100%